## Sheet1
ID | Description | Person | Start date | End date
1 | Start of the Project | Abdalrhman Abdalnasr | 16 \ 11 \2021 | 15\12\2021
1.1 | Client meeting for asking requirements and budget | Abdalrhman Abdalnasr | 17 \ 11 \2021 | 30 \11\2021
1.2 | Meeting with team members | Abdalrhman Abdalnasr | 17 \ 11 \2021 | 15\12\2021
1.3 | Client meeting for discussing risk and threats associated with the project | Abdallh naser | 20 \ 11 \2021 | 11\12\2021
1.4 | Planning | Abdallh naser | 16 \ 11 \2021 | 15\12\2021
1.5 | Assign team and studying the project | Abdalrhman Reda | 20\11\2021 | 10\12\2021
2 | Developing | Abdalrhman Reda | 18\12\2021 | 24\1\2022
2.1 | Buying compatible devices | Abdalrhman Abdalnasr | 20\12\2021 | 30\12\2021
2.2 | Integrating them with each other | Abdalrhman Reda | 25\12\2021 | 10\1\2022
3 | DESIGN AND IMPLEMENTATION | Abdalrham Khaild | 11\1\2022 | 26\2\2022
3.1 | Design UX/UI for IOS and Android | Abdalrahman Abdalnaser | 28\1\2022 | 15\2\2022
3.2 | Design connection between mobiles and GPS | Abdalrhman Khaild | 30\1\2022 | 18\2\2022
3.3 | building GPS connection | Abdalrhman Khaild | 30\1\2022 | 19\2\2022
3.4 | Testing the complete design and casing | Abdalrhman Abdalnasr | 5\2\2022 | 25\2\2022
4 | Implementation | Abdalrhman Abdalnasr | 29\2\2022 | 25\3\2022
4.1 | Installation of devices | Abdalrahman Reda | 1\3\2022 | 15\3\2022
4.2 | Adjusting the system to the real world | Abdalrhman Khaild | 5\3\2022 | 18\3\2022
4.3 | Final testing | Abdalrhman Abdalnasr | 8\3\2022 | 23\3\2022
5 | Training and Handling Over | Abdalrhman Abdalnasr | 28\3\2022 | 23\4\2022
5.1 | Training client | Abdalrhman Abdalnasr | 30\3\2022 | 10\4\2022
5.2 | Handling over of security information (keys/password) | Abdallh naser | 3\4\2022 | 15\4\2022
5.3 | Describing polices | Abdallh naser | 5\4\2022 | 15\4\2022
5.5 | Final report | Abdallh naser | 5\4\2022 | 12\4\2022
5.6 | Closing of project | Abdalrahman Abdalnaser | 16\4\2022 | 23\4\2022